## Sprints
Statuses
DONE
planned
started
blocked
slipped
canceled
| Sprint | S1 | Basic payments | 12 |  | Capacity | 63 | 63 | George | Cristi | Dana | Alan | Tom
[9 empty] | 11 | 13 | 13 | 13 | 13
ID | Status | Epic | Story | Type | Depends | Who | Points
AUTHN01 | DONE | Authentication | Login endpoint in the server | Story |  | George | 8
AUTHN02 | DONE | Authentication | Login form | Story | AUTHN01 | Cristi | 5
AUTHN03 | DONE | Authentication | Forgot password | Story |  | Dana | 5
AUTHN04 | slipped | Authentication | Test Authentication | Story |  | Tom | 5
AUTHZ01 | DONE | Authorization | Role management endpoints in the server | Story |  | Cristi | 3
AUTHZ02 | slipped | Authorization | Authorize endpoint in the server | Story |  | George | 3
AUTHZ03 | slipped | Authorization | Default role for non existing users | Task |  | Dana | 8
AUTHZ04 | DONE | Authorization | Test Authorization | Story |  | Tom | 5
PAY01 | DONE | Payments | Payment methods endpoint | Story |  | Alan | 8
PAY02 | DONE | Payments | Support PayPal | Story |  | Alan | 5
PAY03 | DONE | Payments | Payment form | Story | PAY01 | Cristi | 5
PAY04 | DONE | Payments | Test Payments | Story |  | Tom | 3
| Sprint | S2 | Blah Blah | 11 |  | Capacity | 53 | 53 | George | Cristi | Dana | Alan | Tom
[9 empty] | 3 | 8 | 16 | 13 | 13
ID | Status | Epic | Story | Type | Depends | Who | Points
AUTHN03 | DONE | Authentication | Blah 1 | Story |  | Dana | 5
AUTHN04 | started | Authentication | Blah 2 | Story |  | Tom | 5
AUTHZ01 | DONE | Authorization | Blah 3 | Story |  | Cristi | 3
AUTHZ02 | started | Authorization | Blah 4 | Story |  | George | 3
AUTHZ03 | started | Authorization | Blah 5 | Task |  | Dana | 8
AUTHZ04 | planned | Authorization | Blah 6 | Story |  | Tom | 5
PAY01 | started | Payments | Blah 7 | Story |  | Alan | 8
PAY02 | planned | Payments | Blah 8 | Story |  | Alan | 5
PAY03 | planned | Payments | Blah 9 | Story | PAY01 | Cristi | 5
PAY04 | planned | Payments | Blah 10 | Story |  | Tom | 3
PAY03 | started | Payments | Blah 11 | Story |  | Dana | 3
(copy from above and below and insert before)
|  | Backlog |  | 26 |  | Total | 136 | 0 | George | Cristi | Dana | Alan | Tom
[9 empty] | 0 | 0 | 0 | 0 | 0
ID | Status | Epic | Story | Type | Depends | Who | Points
BAR01 |  | Foo | Baz 01 | Story |  |  | 5
BAR02 |  | Foo | Baz 02 | Story |  |  | 5
BAR03 |  | Foo | Baz 03 | Story |  |  | 3
BAR04 |  | Foo | Baz 04 | Story |  |  | 3
BAR05 |  | Foo | Baz 05 | Task |  |  | 8
BAR06 |  | Foo | Baz 06 | Story |  |  | 5
BAR07 |  | Foo | Baz 07 | Story |  |  | 8
BAR08 |  | Foo | Baz 08 | Story |  |  | 5
BAR09 |  | Foo | Baz 09 | Story | BAR07 |  | 5
BAR10 |  | Foo | Baz 10 | Story |  |  | 3
BAR11 |  | Foo | Baz 11 | Story |  |  | 8
BAR12 |  | Foo | Baz 12 | Story |  |  | 13
BAR13 |  | Foo | Baz 13 | Story |  |  | 2
BAR14 |  | Foo | Baz 14 | Story |  |  | 5
BAR15 |  | Foo | Baz 15 | Task |  |  | 8
BAR16 |  | Foo | Baz 16 | Story |  |  | 3
BAR17 |  | Foo | Baz 17 | Story |  |  | 1
BAR18 |  | Foo | Baz 18 | Story |  |  | 8
BAR19 |  | Foo | Baz 19 | Story |  |  | 5
BAR20 |  | Foo | Baz 20 | Story |  |  | 5
BAR21 |  | Foo | Baz 21 | Story |  |  | 3
BAR22 |  | Foo | Baz 22 | Story |  |  | 1
BAR23 |  | Foo | Baz 23 | Story |  |  | 2
BAR24 |  | Foo | Baz 24 | Story |  |  | 8
BAR25 |  | Foo | Baz 25 | Task |  |  | 13
BAR26 |  | Foo | Baz 26 | Story |  |  | 1
(copy from above and insert before)

## Plan
|  |  |  | Points |  |  |  |  | Items
Sprint | Start | Weeks | Status | Velocity | Margin | Total | Slipped | End | Total | Done | Slipped | Canceled | REF
S1 | 2022-11-21 | 2 | DONE | 50 | 5 | 63 | 16 | 2022-12-09 | 12 | 9 | 3 | 0 | '[agile-sprints.xlsx]Sprints'!$C$10
S2 | 2022-12-12 | 2 | TODO | 50 | 5 | 53 | 0 | 2022-12-30 | 11 | 2 | 0 | 0 | '[agile-sprints.xlsx]Sprints'!$C$27
Backlog | 2022-11-21 | 2 |  |  |  | 136 |  | 2022-12-09 | 26 |  |  |  | '[agile-sprints.xlsx]Sprints'!$C$45
(insert before)
Formulas:
End = WORKDAY([Start],[Weeks]*7)
Start = WORKDAY([End, row above],1)