## Overview
Nr. | Work Item | Description | Tasks Count | Dev Tasks | SV Tasks | Remaining Effort | % Done
1 | Authentication | Authenticate users into the system | 0 | 0 | 0 | 17 | #DIV/0!
2 | Authorization | Authorize users based on their role | 0 | 0 | 0 | 14 | #DIV/0!
3 | Payments | Process payments | 0 | 0 | 0 | 15 | #DIV/0!
(insert before)

## Team
Team | Load / day | Remaining Effort | Remaining Duration | End | Remaining tasks | Remaining days off | Notes
George | 1 | 3 | 6 | 2022-12-01 | 1 | 3
Alan | 1 | 7 | 7 | 2022-12-02 | 1
Dana | 1 | 11 | 11 | 2022-12-08 | 2 | 0
Cristi | 1 | 12 | 12 | 2022-12-09 | 2
Tom | 1 | 13 | 13 | 2022-12-12 | 3
Projected date |  | 46 | 49 | 2022-12-12
Target date |  |  |  | 2019-06-03
Formulas:
End = WORKDAY(TODAY(), IF([Remaining Duration]>0,[Remaining Duration],0))
End = MAX(E2:[End, row above])

## Tasks
ID | Status | Work Item | Task | Type | Depends on | Team | Remaining Effort | Notes
AUTHN01 | DONE | Authentication | Login endpoint in the server | Feature |  | George | 0
AUTHN02 | planned | Authentication | Login form | Feature | AUTHN01 | Cristi | 7
AUTHN03 | planned | Authentication | Forgot password | Feature |  | Dana | 5
AUTHN04 | planned | Authentication | Test Authentication | Testing |  | Tom | 5
AUTHZ01 | DONE | Authorization | Role management endpoints in the server | Feature |  | Cristi | 0
AUTHZ02 | planned | Authorization | Authorize endpoint in the server | Feature |  | George | 3
AUTHZ03 | planned | Authorization | Default role for non existing users | Feature |  | Dana | 6
AUTHZ04 | planned | Authorization | Test Authorization | Testing |  | Tom | 5
PAY01 | planned | Payments | Payment methods endpoint | Feature |  | Alan | 7
PAY02 | DONE | Payments | Support PayPal | Feature |  | Alan | 0
PAY03 | planned | Payments | Payment form | Feature | PAY01 | Cristi | 5
PAY04 | planned | Payments | Test Payments | Testing |  | Tom | 3
[6 empty] | Assigned | 46
[6 empty] | Out | 0
[6 empty] | Total | 46

## ReqTracing
Work Item / Requirement | CR01 | SEC01 | SEC02
Authentication |  |  | x
Authorization |  | x
Payments | x
Covered? | Yes | Yes | Yes