## Velocity
Sprint 5 | Bug Fixing | Mon June 19, 2017 - Friday July 21, 2017
Total issues | 35
Week | Issues solved | Notes
1. June 19 - 23 | 0 | info not gathered for this week
2. June 26 - 30 | 13 | including Week 1
3. July 3 - 7
4. July 10 - 14
5. July 17 - 21
Issues solved | 13
Weeks passed | 2
Current velocity | 6.5
Remaining issues | 22
Remaining weeks | 3
Needed velocity | 7.3333
Slipped issues | 3